## Sheet1
Task | Start Date | Length | End Date
Learning the capabilities of each input device through typical usage | 2016-10-10 | 14 | 2016-10-24
Learning about working in and developing for a 3D environment through Unity tutorials | 2016-10-17 | 21 | 2016-11-07
Learn about the Myo development capabilities | 2016-10-24 | 21 | 2016-11-14
Learn about the Nao Robot and it's programming architecture, potential for virtual robot? | 2016-10-24 | 21 | 2016-11-14
Learn about the Leap Motion development capabilities | 2016-10-24 | 21 | 2016-11-14
Learn about the Oculus Rift development capabilities | 2016-10-31 | 14 | 2016-11-14
Creating simple prototype programs in order to understand the system architecture behind each input device | 2016-11-07 | 28 | 2016-12-05
Define the project specification and outline a system architecture | 2016-12-05 | 7 | 2016-12-12
Begin development on a polished deliverable to solidify and showcase the Myo/LM devices as input mechanisms | 2016-11-21 | 42 | 2017-01-02
Crossing a river realisation prototype? | 2016-11-21 | 42 | 2017-01-02
Move on to programming the complete project | 2017-01-02 | 1 | 2017-01-03
Arm movement | 2017-01-02 | 1 | 2017-01-03
Head movement | 2017-01-02 | 1 | 2017-01-03
Leg movement | 2017-01-02 | 1 | 2017-01-03
Camera feed | 2017-01-02 | 1 | 2017-01-03
Phase 1 - Input Devices | 2016-10-03 | 84 | 2016-12-26
Phase 2 - Output Devices | 2016-11-21 | 91 | 2017-02-20
Phase 3 - Project Deliverable | 2017-01-16 | 98 | 2017-04-24
Documentation | 2016-11-09 | 173 | 2017-05-01